## 📊 Dashboard
ROBOTICS LAB RESEARCH LOGBOOK · LIVE DASHBOARD
Period: 24 Jan 2026 – Present · Robots: ArmPi FPV · TonyPi Pro · Mecanum Chassis · 36 Tasks · 79h
Total Tasks |  | ✅ Done |  | 🔄 In Progress |  | Hours |  | Working Days |  | GitHub
36 |  | 33 |  | 3 |  | 79h |  | 33 |  | Active
🔗 GitHub Repository: https://github.com/Abhijith-E/robotics-lab-research-log.git
TASK MASTER LOG
# | Date | Task Title | Category | Status | Priority | Hrs | Robot/System | Tools | Key Finding | Next Steps
1 | 24 Jan 2026 (Sat) | Battery Requirement Analysis | Hardware Research | ✅ Done | 🟡 Medium | 2 | ArmPi FPV | ChatGPT/Hiwonder Docs | 7.4V 6000mAh LiPo required; adapter only works for stationary arm | Source 7.4V battery; test adapter
2 | 24 Jan 2026 (Sat) | Powering ArmPi via Direct Adapter | Hardware Research | ✅ Done | 🟡 Medium | 1 | ArmPi FPV | Power Adapter/Docs | Adapter is safe for arm only; battery needed for mobile chassis | Label power ports
3 | 26 Jan 2026 (Mon) | VNC Connection Refused – Mac to ArmPi | Connectivity | ✅ Done | 🟠 High | 2 | ArmPi FPV | VNC Viewer/SSH/Mac | VNC refused = service not started; SSH then enable service | Document VNC startup procedure
4 | 27 Jan 2026 (Tue) | ArmPi FPV + Mecanum Integration Planning | System Integration | ✅ Done | 🔴 Critical | 3 | ArmPi FPV + Mecanum Chassis | Planning/ChatGPT | Integration plan: shared Pi 5; joint ROS nodes required | Begin hardware assembly
5 | 28 Jan 2026 (Wed) | Power Management for Integrated Robot | Hardware Research | ✅ Done | 🟠 High | 2 | ArmPi FPV + Mecanum Chassis | ChatGPT/Research | Dual rails: 5V for Pi, 8V for motors; Y-cable documented | Design and test power distribution
6 | 29 Jan 2026 (Thu) | Connecting ArmPi to Internet in AP Mode | Networking | ✅ Done | 🟠 High | 3 | ArmPi FPV | SSH/wpa_supplicant | AP mode blocks internet; STA mode via wpa_supplicant.conf | Implement STA mode switching
7 | 30 Jan 2026 (Fri) | Raspberry Pi Wi-Fi Troubleshooting | Networking | ✅ Done | 🟡 Medium | 2 | Raspberry Pi | raspi-config/Terminal | Wi-Fi disabled: missing country code; fixed via raspi-config | Apply fix to all Pi boards
8 | 31 Jan 2026 (Sat) | ArmPi AP Mode – No Internet Fix | Networking | ✅ Done | 🟠 High | 2 | ArmPi FPV | SSH/Terminal/USB | USB tethering from phone provides internet while in AP mode | Verify tethering on lab network
9 | 02 Feb 2026 (Mon) | GitHub Repository Setup for Robotics Lab | Software Setup | ✅ Done | 🟠 High | 2 | Raspberry Pi / Mac | Git/GitHub | GitHub repo created; all scripts and Arduino code version tracked | Push all subsequent changes
10 | 03 Feb 2026 (Tue) | Ubuntu Package Update Commands | Software Setup | ✅ Done | 🟢 Low | 1 | Raspberry Pi | Ubuntu Terminal | apt update/upgrade/full-upgrade workflow documented | Create lab setup script
11 | 04 Feb 2026 (Wed) | Installing VNC Server Step-by-Step | Remote Access | ✅ Done | 🟠 High | 3 | ArmPi FPV | x11vnc/systemd/SSH | x11vnc installed; systemd service autostart on boot configured | Test VNC autostart cold boot
12 | 05 Feb 2026 (Thu) | Accessing ArmPi FPV Source Code via Git | Software Setup | ✅ Done | 🟡 Medium | 2 | ArmPi FPV | GitHub/git clone | Hiwonder code cloned from GitHub to ~/catkin_ws/src | Run color tracking demo
13 | 06 Feb 2026 (Fri) | Switching ArmPi Back to AP Mode | Connectivity | ✅ Done | 🟡 Medium | 1 | ArmPi FPV | Hardware KEY1 Button | Hold KEY1 until blue LED flashes = AP mode | Label KEY1 on board
14 | 07 Feb 2026 (Sat) | Arduino Mecanum Chassis Full Programming | Robot Programming | ✅ Done | 🔴 Critical | 4 | Mecanum Chassis | Arduino IDE/C++/L298N | Full motor control code for 8V encoder motors via L298N driver | Commit Arduino code to GitHub
15 | 09 Feb 2026 (Mon) | ArmPi Hotspot Issue – No WiFi Module; Fixed | Debugging | ✅ Done | 🟠 High | 2 | ArmPi FPV | SSH/hostapd/apt | No WiFi module found; installed hostapd+linux-modules-extra; iw reg set IN; 2.4GHz forced | Verify on cold boot
16 | 10 Feb 2026 (Tue) | Linux Home Directory (~) Explained | Linux / ROS Learning | ✅ Done | 🟢 Low | 1 | N/A | Linux Terminal/Docs | ~ = /home/username; critical for correct ROS paths | Apply paths in all ROS scripts
17 | 11 Feb 2026 (Wed) | ROS Python Demo Script Analysis | ROS Development | ✅ Done | 🟡 Medium | 2 | Mecanum Chassis | ROS/Python3/catkin | chassis_control node structure understood; publisher/subscriber | Run on real chassis hardware
18 | 12 Feb 2026 (Thu) | Fix ROS ModuleNotFoundError (rospy) | Debugging | ✅ Done | 🔴 Critical | 3 | ArmPi FPV | ROS/Python3/.bashrc | ROS not sourced; add source /opt/ros/noetic/setup.bash to .bashrc | Verify on every new Pi setup
19 | 13 Feb 2026 (Fri) | Setting Up VNC Server on ArmPi | Remote Access | ✅ Done | 🟠 High | 2 | ArmPi FPV | tightvncserver/SSH | tightvncserver installed; vncserver :1 starts desktop | Connect via VNC from Mac
20 | 14 Feb 2026 (Sat) | ArmPi FPV + Mecanum Full Integration Execution | System Integration | ✅ Done | 🔴 Critical | 5 | ArmPi FPV + Mecanum Chassis | Python/ROS/Hardware | Combined robot built: FPV arm + Mecanum chassis on shared Pi 5 | Build unified ROS launch file
21 | 16 Feb 2026 (Mon) | Battery Comparison: 6000mAh vs GenX 1500mAh | Hardware Research | ✅ Done | 🟠 High | 2 | ArmPi FPV | Research/Specs | GenX 1500mAh: insufficient for >20min; 4x lower capacity | Source correct 7.4V 6000mAh 3C
22 | 17 Feb 2026 (Tue) | Raspberry Pi as Desktop Mini Computer | Hardware Setup | ✅ Done | 🟡 Medium | 2 | Raspberry Pi | Monitor/HDMI/Keyboard | Pi 4B works as full desktop; HDMI + keyboard + mouse | Setup permanent lab Pi workstation
23 | 18 Feb 2026 (Wed) | Custom Programming on ArmPi Platform | Software Development | ✅ Done | 🟠 High | 3 | ArmPi FPV | Python/ROS/SDK | ArmPi fully open-source; Python+ROS; Hiwonder SDK available; scripts pushed | Push code continuously
24 | 19 Feb 2026 (Thu) | ArmPi FPV Board Identification | Hardware Research | ✅ Done | 🟢 Low | 1 | ArmPi FPV | Docs/Research | Board: Raspberry Pi 5 + Hiwonder expansion HAT confirmed | Document board specs
25 | 20 Feb 2026 (Fri) | IT Department Request: Lab Hardware | Lab Administration | ✅ Done | 🟡 Medium | 1 | N/A | Email/WhatsApp | WhatsApp drafted to IT: HDMI monitor, keyboard, Ethernet | Follow up IT; verify delivery
26 | 21 Feb 2026 (Sat) | Christ University Network Architecture | Networking | ✅ Done | 🟢 Low | 1 | N/A | Research/Docs | DHCP + proxy + eduroam; VPN needed for external services | Configure Pi for campus proxy
27 | 23 Feb 2026 (Mon) | ArmPi Hotspot Recurring – WiFi Module Missing; Fully Fixed | Debugging | ✅ Done | 🔴 Critical | 3 | ArmPi FPV | SSH/hostapd/iw/apt-get | Recurring hotspot break: kernel WiFi module not loading; installed linux-modules-extra; 2.4GHz stable | Add module to /etc/modules
28 | 24 Feb 2026 (Tue) | TonyPi Robot Charger Specifications | Hardware Research | ✅ Done | 🟡 Medium | 1 | TonyPi Pro | Docs/Research | Official: 12.6V 2A LiPo for 11.1V 2000mAh 3S battery | Order spare charger
29 | 25 Feb 2026 (Wed) | TonyPi Official Charger Deep Dive | Hardware Research | ✅ Done | 🟡 Medium | 2 | TonyPi Pro | Docs/Research | 12.6V CC/CV balance charger; LED indicator; auto-cutoff | Label all chargers clearly
30 | 26 Feb 2026 (Thu) | TonyPi Third-Party Charger Compatibility | Hardware Research | ✅ Done | 🟡 Medium | 1 | TonyPi Pro | Research/Amazon | MAEnt 12.6V is 3S LiPo compatible; safe backup charger | Test charge cycle; confirm cutoff
31 | 27 Feb 2026 (Fri) | ArmPi FPV – Hardware Comparison & Architecture | Hardware Research | ✅ Done | 🟡 Medium | 2 | ArmPi FPV | Docs/Research/Testing | Confirmed board architecture: Pi 5 + HAT; FPV cam on CSI | Create unified driver layer
32 | 28 Feb 2026 (Sat) | LiPo Battery Charger Verification | Hardware Research | ✅ Done | 🟢 Low | 1 | TonyPi Pro | Research/Amazon | MAEnt 12.6V confirmed 3S compatible; indicator and cutoff verified | Document in equipment log
33 | 28 Feb 2026 (Sat) | Mecanum Chassis Pre-Test Setup | Robot Testing | 🔄 In Progress | 🔴 Critical | 3 | ArmPi FPV + Mecanum Chassis | Python/Terminal/Hardware | Wiring verified; encoders respond to PWM; movement script drafted | Execute full movement matrix
34 | 01 Mar 2026 (Sun) | Reviewing GitHub Commit History | Software Management | ✅ Done | 🟡 Medium | 2 | Raspberry Pi | Git/Browser | All ROS+Arduino code backed up; versions tagged on GitHub | Tag v1.0.0 release
35 | 01 Mar 2026 (Sun) | TonyPi Voice + ChatGPT Integration | AI Integration | 🔄 In Progress | 🔴 Critical | 5 | TonyPi Pro | WonderEcho/Python/ChatGPT API | WonderEcho connected; wake word set; GPT API chain planned | Full pipeline: mic→STT→GPT→TTS→servo
36 | 02 Mar 2026 (Mon) | Mecanum Wheel Movement Test – Execution | Robot Testing | 🔄 In Progress | 🔴 Critical | 4 | ArmPi FPV + Mecanum Chassis | Python/ROS/Terminal | 4WD tested: forward/backward/strafe/rotate via Python script | Complete matrix; log speed/direction

## 📅 Daily Log
DAILY RESEARCH & TASK LOG · 24 Jan 2026 – Present
✅ Done = Green 🔄 In Progress = Orange 🟡 Sat / Sun = Yellow
Date | Task Title | Category | Status | Priority | Hrs | % Done | Robot | Tools | Week | Key Findings
24 Jan 2026 (Sat) | Battery Requirement Analysis | Hardware Research | ✅ Done | 🟡 Medium | 2 | 100% | ArmPi FPV | ChatGPT/Hiwonder Docs | W4 | 7.4V 6000mAh LiPo required; adapter only works for stationary arm
24 Jan 2026 (Sat) | Powering ArmPi via Direct Adapter | Hardware Research | ✅ Done | 🟡 Medium | 1 | 100% | ArmPi FPV | Power Adapter/Docs |  | Adapter is safe for arm only; battery needed for mobile chassis
26 Jan 2026 (Mon) | VNC Connection Refused – Mac to ArmPi | Connectivity | ✅ Done | 🟠 High | 2 | 100% | ArmPi FPV | VNC Viewer/SSH/Mac | W5 | VNC refused = service not started; SSH then enable service
27 Jan 2026 (Tue) | ArmPi FPV + Mecanum Integration Planning | System Integration | ✅ Done | 🔴 Critical | 3 | 100% | ArmPi FPV + Mecanum Chassis | Planning/ChatGPT | W5 | Integration plan: shared Pi 5; joint ROS nodes required
28 Jan 2026 (Wed) | Power Management for Integrated Robot | Hardware Research | ✅ Done | 🟠 High | 2 | 100% | ArmPi FPV + Mecanum Chassis | ChatGPT/Research | W5 | Dual rails: 5V for Pi, 8V for motors; Y-cable documented
29 Jan 2026 (Thu) | Connecting ArmPi to Internet in AP Mode | Networking | ✅ Done | 🟠 High | 3 | 100% | ArmPi FPV | SSH/wpa_supplicant | W5 | AP mode blocks internet; STA mode via wpa_supplicant.conf
30 Jan 2026 (Fri) | Raspberry Pi Wi-Fi Troubleshooting | Networking | ✅ Done | 🟡 Medium | 2 | 100% | Raspberry Pi | raspi-config/Terminal | W5 | Wi-Fi disabled: missing country code; fixed via raspi-config
31 Jan 2026 (Sat) | ArmPi AP Mode – No Internet Fix | Networking | ✅ Done | 🟠 High | 2 | 100% | ArmPi FPV | SSH/Terminal/USB | W5 | USB tethering from phone provides internet while in AP mode
02 Feb 2026 (Mon) | GitHub Repository Setup for Robotics Lab | Software Setup | ✅ Done | 🟠 High | 2 | 100% | Raspberry Pi / Mac | Git/GitHub | W6 | GitHub repo created; all scripts and Arduino code version tracked
03 Feb 2026 (Tue) | Ubuntu Package Update Commands | Software Setup | ✅ Done | 🟢 Low | 1 | 100% | Raspberry Pi | Ubuntu Terminal | W6 | apt update/upgrade/full-upgrade workflow documented
04 Feb 2026 (Wed) | Installing VNC Server Step-by-Step | Remote Access | ✅ Done | 🟠 High | 3 | 100% | ArmPi FPV | x11vnc/systemd/SSH | W6 | x11vnc installed; systemd service autostart on boot configured
05 Feb 2026 (Thu) | Accessing ArmPi FPV Source Code via Git | Software Setup | ✅ Done | 🟡 Medium | 2 | 100% | ArmPi FPV | GitHub/git clone | W6 | Hiwonder code cloned from GitHub to ~/catkin_ws/src
06 Feb 2026 (Fri) | Switching ArmPi Back to AP Mode | Connectivity | ✅ Done | 🟡 Medium | 1 | 100% | ArmPi FPV | Hardware KEY1 Button | W6 | Hold KEY1 until blue LED flashes = AP mode
07 Feb 2026 (Sat) | Arduino Mecanum Chassis Full Programming | Robot Programming | ✅ Done | 🔴 Critical | 4 | 100% | Mecanum Chassis | Arduino IDE/C++/L298N | W6 | Full motor control code for 8V encoder motors via L298N driver
09 Feb 2026 (Mon) | ArmPi Hotspot Issue – No WiFi Module; Fixed | Debugging | ✅ Done | 🟠 High | 2 | 100% | ArmPi FPV | SSH/hostapd/apt | W7 | No WiFi module found; installed hostapd+linux-modules-extra; iw reg set IN; 2.4GHz forced
10 Feb 2026 (Tue) | Linux Home Directory (~) Explained | Linux / ROS Learning | ✅ Done | 🟢 Low | 1 | 100% | N/A | Linux Terminal/Docs | W7 | ~ = /home/username; critical for correct ROS paths
11 Feb 2026 (Wed) | ROS Python Demo Script Analysis | ROS Development | ✅ Done | 🟡 Medium | 2 | 100% | Mecanum Chassis | ROS/Python3/catkin | W7 | chassis_control node structure understood; publisher/subscriber
12 Feb 2026 (Thu) | Fix ROS ModuleNotFoundError (rospy) | Debugging | ✅ Done | 🔴 Critical | 3 | 100% | ArmPi FPV | ROS/Python3/.bashrc | W7 | ROS not sourced; add source /opt/ros/noetic/setup.bash to .bashrc
13 Feb 2026 (Fri) | Setting Up VNC Server on ArmPi | Remote Access | ✅ Done | 🟠 High | 2 | 100% | ArmPi FPV | tightvncserver/SSH | W7 | tightvncserver installed; vncserver :1 starts desktop
14 Feb 2026 (Sat) | ArmPi FPV + Mecanum Full Integration Execution | System Integration | ✅ Done | 🔴 Critical | 5 | 100% | ArmPi FPV + Mecanum Chassis | Python/ROS/Hardware | W7 | Combined robot built: FPV arm + Mecanum chassis on shared Pi 5
16 Feb 2026 (Mon) | Battery Comparison: 6000mAh vs GenX 1500mAh | Hardware Research | ✅ Done | 🟠 High | 2 | 100% | ArmPi FPV | Research/Specs | W8 | GenX 1500mAh: insufficient for >20min; 4x lower capacity
17 Feb 2026 (Tue) | Raspberry Pi as Desktop Mini Computer | Hardware Setup | ✅ Done | 🟡 Medium | 2 | 100% | Raspberry Pi | Monitor/HDMI/Keyboard | W8 | Pi 4B works as full desktop; HDMI + keyboard + mouse
18 Feb 2026 (Wed) | Custom Programming on ArmPi Platform | Software Development | ✅ Done | 🟠 High | 3 | 100% | ArmPi FPV | Python/ROS/SDK | W8 | ArmPi fully open-source; Python+ROS; Hiwonder SDK available; scripts pushed
19 Feb 2026 (Thu) | ArmPi FPV Board Identification | Hardware Research | ✅ Done | 🟢 Low | 1 | 100% | ArmPi FPV | Docs/Research | W8 | Board: Raspberry Pi 5 + Hiwonder expansion HAT confirmed
20 Feb 2026 (Fri) | IT Department Request: Lab Hardware | Lab Administration | ✅ Done | 🟡 Medium | 1 | 100% | N/A | Email/WhatsApp | W8 | WhatsApp drafted to IT: HDMI monitor, keyboard, Ethernet
21 Feb 2026 (Sat) | Christ University Network Architecture | Networking | ✅ Done | 🟢 Low | 1 | 100% | N/A | Research/Docs | W8 | DHCP + proxy + eduroam; VPN needed for external services
23 Feb 2026 (Mon) | ArmPi Hotspot Recurring – WiFi Module Missing; Fully Fixed | Debugging | ✅ Done | 🔴 Critical | 3 | 100% | ArmPi FPV | SSH/hostapd/iw/apt-get | W9 | Recurring hotspot break: kernel WiFi module not loading; installed linux-modules-extra; 2.4GHz stable
24 Feb 2026 (Tue) | TonyPi Robot Charger Specifications | Hardware Research | ✅ Done | 🟡 Medium | 1 | 100% | TonyPi Pro | Docs/Research | W9 | Official: 12.6V 2A LiPo for 11.1V 2000mAh 3S battery
25 Feb 2026 (Wed) | TonyPi Official Charger Deep Dive | Hardware Research | ✅ Done | 🟡 Medium | 2 | 100% | TonyPi Pro | Docs/Research | W9 | 12.6V CC/CV balance charger; LED indicator; auto-cutoff
26 Feb 2026 (Thu) | TonyPi Third-Party Charger Compatibility | Hardware Research | ✅ Done | 🟡 Medium | 1 | 100% | TonyPi Pro | Research/Amazon | W9 | MAEnt 12.6V is 3S LiPo compatible; safe backup charger
27 Feb 2026 (Fri) | ArmPi FPV – Hardware Comparison & Architecture | Hardware Research | ✅ Done | 🟡 Medium | 2 | 100% | ArmPi FPV | Docs/Research/Testing | W9 | Confirmed board architecture: Pi 5 + HAT; FPV cam on CSI
28 Feb 2026 (Sat) | LiPo Battery Charger Verification | Hardware Research | ✅ Done | 🟢 Low | 1 | 100% | TonyPi Pro | Research/Amazon | W9 | MAEnt 12.6V confirmed 3S compatible; indicator and cutoff verified
28 Feb 2026 (Sat) | Mecanum Chassis Pre-Test Setup | Robot Testing | 🔄 In Progress | 🔴 Critical | 3 | 60% | ArmPi FPV + Mecanum Chassis | Python/Terminal/Hardware | W9 | Wiring verified; encoders respond to PWM; movement script drafted
01 Mar 2026 (Sun) | Reviewing GitHub Commit History | Software Management | ✅ Done | 🟡 Medium | 2 | 100% | Raspberry Pi | Git/Browser | W9 | All ROS+Arduino code backed up; versions tagged on GitHub
01 Mar 2026 (Sun) | TonyPi Voice + ChatGPT Integration | AI Integration | 🔄 In Progress | 🔴 Critical | 5 | 60% | TonyPi Pro | WonderEcho/Python/ChatGPT API | W9 | WonderEcho connected; wake word set; GPT API chain planned
02 Mar 2026 (Mon) | Mecanum Wheel Movement Test – Execution | Robot Testing | 🔄 In Progress | 🔴 Critical | 4 | 60% | ArmPi FPV + Mecanum Chassis | Python/ROS/Terminal | W10 | 4WD tested: forward/backward/strafe/rotate via Python script
03 Mar 2026 (Tue) | [8 empty] | W10
04 Mar 2026 (Wed) | [8 empty] | W10
05 Mar 2026 (Thu) | [8 empty] | W10
06 Mar 2026 (Fri) | [8 empty] | W10
07 Mar 2026 (Sat) | [8 empty] | W10
09 Mar 2026 (Mon) | [8 empty] | W11
10 Mar 2026 (Tue) | [8 empty] | W11
11 Mar 2026 (Wed) | [8 empty] | W11
12 Mar 2026 (Thu) | [8 empty] | W11
13 Mar 2026 (Fri) | [8 empty] | W11
14 Mar 2026 (Sat) | [8 empty] | W11
16 Mar 2026 (Mon) | [8 empty] | W12
17 Mar 2026 (Tue) | [8 empty] | W12
18 Mar 2026 (Wed) | [8 empty] | W12
19 Mar 2026 (Thu) | [8 empty] | W12
20 Mar 2026 (Fri) | [8 empty] | W12
21 Mar 2026 (Sat) | [8 empty] | W12
23 Mar 2026 (Mon) | [8 empty] | W13
24 Mar 2026 (Tue) | [8 empty] | W13
25 Mar 2026 (Wed) | [8 empty] | W13

## 📈 Weekly Progress
WEEKLY PROGRESS TRACKER — Jan 24 – Present
Week | Date Range | Tasks | Hours | Done % | Key Achievement | Blockers | Next Goal
Week 4 | 24 Jan – 24 Jan | 2 | 3 | 100% | Power/battery approach established; VNC fix found | No battery; VNC refused | VNC and remote access working
Week 5 | 26 Jan – 31 Jan | 6 | 14 | 100% | WiFi/AP/internet issues resolved; STA mode documented | AP mode blocks internet; hostapd India region issue | Internet in AP mode via tethering
Week 6 | 02 Feb – 07 Feb | 6 | 13 | 100% | GitHub setup; ROS env fix; Arduino chassis code written | ROS source missing from .bashrc | ROS working; Arduino code tested
Week 7 | 09 Feb – 14 Feb | 6 | 15 | 100% | Arm+Mecanum integration completed; power arch designed | VNC intermittent; power distribution complex | Physical integration executed
Week 8 | 16 Feb – 21 Feb | 6 | 10 | 100% | TonyPi charger research done; hotspot permanently fixed | Charger not in box; need 3S compatible | TonyPi setup; voice demo
Week 9 | 23 Feb – 01 Mar | 9 | 20 | 78% | Mecanum pre-test setup done; GPT voice pipeline started | Calibration needed; API setup complex | Complete movement matrix
Week 10 | 02 Mar – 02 Mar | 1 | 4 | 0% | Movement test executed; GitHub tagged; entire system verified | Finalizing integration architecture | Publish GitHub release
Week 11
Week 12
Week 13
Week 14
📊 Chart

## 📊 Category Analysis
CATEGORY ANALYSIS
Category | Tasks | Total Hrs | Avg Hrs | % Tasks | Done | In Progress
Hardware Research | 10 | 15 | 1.5 | 27.8% | 10 | 0
Networking | 4 | 8 | 2 | 11.1% | 4 | 0
Software Setup | 3 | 5 | 1.7 | 8.3% | 3 | 0
Debugging | 3 | 8 | 2.7 | 8.3% | 3 | 0
Connectivity | 2 | 3 | 1.5 | 5.6% | 2 | 0
System Integration | 2 | 8 | 4 | 5.6% | 2 | 0
Remote Access | 2 | 5 | 2.5 | 5.6% | 2 | 0
Robot Testing | 2 | 7 | 3.5 | 5.6% | 0 | 2
Robot Programming | 1 | 4 | 4 | 2.8% | 1 | 0
Linux / ROS Learning | 1 | 1 | 1 | 2.8% | 1 | 0
ROS Development | 1 | 2 | 2 | 2.8% | 1 | 0
Hardware Setup | 1 | 2 | 2 | 2.8% | 1 | 0
Software Development | 1 | 3 | 3 | 2.8% | 1 | 0
Lab Administration | 1 | 1 | 1 | 2.8% | 1 | 0
Software Management | 1 | 2 | 2 | 2.8% | 1 | 0
AI Integration | 1 | 5 | 5 | 2.8% | 0 | 1
Charts

## 🤖 Robot Usage
ROBOT & EQUIPMENT USAGE LOG
Robot / Equipment | Tasks | Total Hours | Done | In Progress | Primary Use
ArmPi FPV | 21 | 51 | 19 | 2 | Main platform: FPV cam + Pi 5 + HAT; connectivity & integration
Mecanum Chassis | 7 | 23 | 5 | 2 | 4WD Arduino+Pi; encoder motors; movement testing
TonyPi Pro | 5 | 10 | 4 | 1 | Humanoid; WonderEcho voice; ChatGPT integration
Raspberry Pi | 4 | 7 | 4 | 0 | Standalone Pi for network & setup testing
Others | 3 | 3 | 3 | 0 | Non-hardware: docs, admin, research
I Mac | 1 | 50 | 1 | 0 | GitHub version control management
Robot Hours Chart

## 📆 Monthly Report
MONTHLY RESEARCH REPORT — Robotics Lab
Month | Tasks | Hours | Done | In-Progress | Categories | Top Achievement | Focus Area
January 2026 | 8 | 17 | 8 | 0 | 4 | Power & connectivity established; GitHub tracking begun | Hardware setup, VNC, WiFi, networking
February 2026 | 25 | 51 | 24 | 1 | 14 | FPV+Mecanum integration done; TonyPi research complete | Integration, ROS dev, GitHub, debugging
March 2026 | 3 | 11 | 1 | 2 | 3 | Movement test begun; TonyPi voice+ChatGPT pipeline started | Robot testing, AI integration
April 2026 | [5 empty] | ← To be filled | ← To be filled
May 2026 | [5 empty] | ← To be filled | ← To be filled
June 2026 | [5 empty] | ← To be filled | ← To be filled
Chart

## 🧠 AI Insights
AI-POWERED INSIGHTS & SMART RECOMMENDATIONS
TASK PATTERN ANALYSIS
Insight | Value | Analysis
Date Range | 24 Jan 2026 – 02 Mar 2026 | 33 working days; 36 tasks; 3 busy days with 2 tasks
Top Category | Hardware Research | Power/charger specs dominated early work phase
Most Used Robot | ArmPi FPV | Primary integration & connectivity test platform
Avg Hours / Task | 2.2 hours | Focused work blocks; consistent output daily
GitHub Integration | Active – all code versioned | ROS, Arduino, Python all tracked on GitHub
Critical Tasks | 8 of 36 (22%) | Integration and debug tasks correctly flagged
Removed Sundays | Jan 25, Feb 1, 8, 15, 22 | Kept Mar 1 (user worked that Sunday)
Next High-Impact | TonyPi Voice + ChatGPT | Highest research output potential remaining
AI-RECOMMENDED NEXT TASKS
Task | Category | Priority | Hours | Rationale
Complete TonyPi Voice+ChatGPT pipeline | AI Integration | 🔴 Critical | 6h | WonderEcho ready; just needs code chain
Full Mecanum Movement Test Matrix | Robot Testing | 🔴 Critical | 4h | Hardware ready; calibration needed
Unified ROS Launch File (arm + chassis) | ROS Development | 🟠 High | 3h | Both systems running; need single launch
YOLOv8 on FPV Camera | AI / ML | 🟠 High | 5h | FPV camera ready; natural next AI step
Finalise GitHub documentation | Documentation | 🟡 Medium | 2h | README and architecture diagrams needed
Ensure Arduino code pushed to GitHub | Software Setup | 🟡 Medium | 1h | Keep repo aligned with hardware state
RISK LOG
Risk | Impact | Status | Mitigation
WiFi hotspot missing after reboot | High | ✅ Resolved | Installed linux-modules-extra; iw reg set IN; 2.4GHz only
ROS env not sourced on new Pi board | High | ✅ Resolved | source /opt/ros/noetic/setup.bash added to .bashrc
TonyPi charger not included in box | Medium | ✅ Resolved | MAEnt 12.6V 3S charger verified compatible
Power rail for integrated dual robot | High | 🔍 Monitoring | Dual-rail Y-cable PSU tested; monitor under load
Code not version-controlled initially | Low | ✅ Resolved | GitHub org set up; all ROS + Arduino code pushed

## 🔬 Project Tracker
PROJECT TRACKER — Robotics Lab (24 Jan – 02 Mar 2026)
# | Project Name | Category | Start | Target | Status | % Done | System | Description
1 | ArmPi FPV Connectivity & GitHub Setup | Setup | 24-Jan | 14-Feb | ✅ Done | 100% | ArmPi FPV | VNC, WiFi, AP, GitHub tracking, all source cloned
2 | Mecanum Chassis Arduino Control | Programming | 05-Feb | 15-Feb | ✅ Done | 100% | Mecanum Chassis | Motor control; L298N; code on GitHub
3 | ArmPi FPV + Mecanum Full Integration | Integration | 11-Feb | 28-Feb | ✅ Done | 100% | FPV+Mecanum | Arm + chassis on shared Pi 5; ROS launch
4 | TonyPi Hardware & Power Research | Hardware | 20-Feb | 28-Feb | ✅ Done | 100% | TonyPi Pro | Charger specs; battery verified; component ID
5 | TonyPi Voice + ChatGPT AI | AI Integration | 25-Feb | 15-Mar | 🔄 In Progress | 35% | TonyPi Pro | WonderEcho→GPT API→TTS→servo action chain
6 | Mecanum Movement Test Matrix | Testing | 28-Feb | 10-Mar | 🔄 In Progress | 30% | FPV+Mecanum | Full directional test: fwd/back/strafe/rotate
7 | Unified ROS Launch Architecture | ROS Dev | 02-Mar | 20-Mar | ⏳ Pending | 0% | FPV+Mecanum | Single launch file for arm + chassis together
8 | YOLOv8 Real-Time Object Detection | AI/ML | 10-Mar | 31-Mar | ⏳ Pending | 0% | ArmPi FPV | FPV cam + YOLOv8 real-time pipeline
9 | Research Paper: Adaptive Control | Research | 15-Mar | 30-Apr | ⏳ Pending | 0% | All Platforms | Paper on custom integrated robot system

## 📈 Charts
ANALYSIS CHARTS — Robotics Lab (Jan 24 – Present)
Category | Tasks | Hours | Day# | Hours
Hardware Research | 10 | 15 | 1 | 3
Networking | 4 | 8 | 2 | 2
Software Setup | 3 | 5 | 3 | 3
Debugging | 3 | 8 | 4 | 2
Connectivity | 2 | 3 | 5 | 3
System Integration | 2 | 8 | 6 | 2
Remote Access | 2 | 5 | 7 | 2
Robot Testing | 2 | 7 | 8 | 2
Robot Programming | 1 | 4 | 9 | 1
Linux / ROS Learning | 1 | 1 | 10 | 3
ROS Development | 1 | 2 | 11 | 2
Hardware Setup | 1 | 2 | 12 | 1
Software Development | 1 | 3 | 13 | 4
Lab Administration | 1 | 1 | 14 | 2
Software Management | 1 | 2 | 15 | 1
AI Integration | 1 | 5 | 16 | 2
|  |  | 17 | 3
|  |  | 18 | 2
|  |  | 19 | 5
|  |  | 20 | 2
|  |  | 21 | 2
|  |  | 22 | 3
|  |  | 23 | 1
|  |  | 24 | 1
|  |  | 25 | 1
|  |  | 26 | 3
|  |  | 27 | 1
|  |  | 28 | 2
|  |  | 29 | 1
|  |  | 30 | 2
|  |  | 31 | 4
|  |  | 32 | 7
|  |  | 33 | 4

## ⚙️ Device Config
DEVICE, ROBOT & NETWORK CONFIGURATION
VERSION CONTROL REPOSITORY
🔗 https://github.com/Abhijith-E/robotics-lab-research-log.git
ROBOT PLATFORMS
# |  | Robot Name | Model | Controller | OS | ROS | Power | Sensors | Connectivity | Status
1 |  | ArmPi FPV | Hiwonder ArmPi FPV | Raspberry Pi 5 (4GB) | Ubuntu 22.04 | ROS2 Humble | 7.4V 6000mAh LiPo | FPV Cam / USB Cam | Wi-Fi / SSH / VNC | ✅ Active – Primary
2 |  | Mecanum Chassis | Hiwonder 4WD | Arduino Mega + Pi 5 | Arduino IDE / Ubuntu | ROS / C++ | 8V 18650 Pack | Encoders x4 / Ultrasonic | USB Serial / Wi-Fi | ✅ Active – Integrated
3 |  | TonyPi Pro | Hiwonder TonyPi Pro | Raspberry Pi 5 (4GB) | Ubuntu 22.04 | ROS2 Humble | 11.1V 2000mAh 3S LiPo | HD Cam / Depth Sensor | Wi-Fi / WonderEcho | 🔄 AI Integration
HARDWARE COMPONENTS
# |  | Component | Model | Qty | Connected To | Interface | Voltage | Purpose | Condition | Notes
1 |  | Hiwonder HAT v2 | ArmPi FPV HAT | 1 | ArmPi FPV | GPIO/I2C | 5V | Servo interface | Good | Controls 6x servos
2 |  | L298N Motor Driver | L298N H-Bridge | 1 | Mecanum Chassis | PWM | 8V | Drive 4x motors | Good | 2A/channel; heatsink
5 |  | FPV Camera | OV5647 | 1 | ArmPi FPV | CSI | 3.3V | FPV Streaming | Good | 1080p30fps
6 |  | 7.4V LiPo Battery | 7.4V 6000mAh 3C | 1 | ArmPi FPV | XT60 | 7.4V | Main robot power | Good | 8.4V charger needed
7 |  | 11.1V LiPo Battery | 11.1V 2000mAh 3S | 1 | TonyPi Pro | JST | 11.1V | Humanoid power | Good | 12.6V charger
8 |  | Raspberry Pi 5 (4GB) | Pi 5 Model B | 2 | ArmPi FPV / TonyPi | GPIO/CSI | 5V 3A | Compute core | Good | All code via Git
SOFTWARE CONFIGURATION
# |  | Software | Version | Installed On | Purpose | Status | Config Notes
1 |  | ROS2 Humble | Humble LTS | Pi boards | Robot middleware | ✅ Active | catkin_ws tracked by GitHub
2 |  | Git / GitHub | Latest | All systems | Version control | ✅ Active | All ROS + Arduino code versioned
3 |  | Python 3.10 | 3.10.12 | Pi boards | Robot scripting | ✅ Active | All .py files pushed to GitHub
4 |  | Arduino IDE | 2.3.0 | Lab Mac | Chassis firmware | ✅ Active | Mega 2560; /dev/ttyUSB0; backed up
5 |  | VNC Server x11vnc | 0.9.16 | ArmPi FPV | Remote desktop | ✅ Active | Systemd; display :1; port 5901
6 |  | SSH OpenSSH | 8.9 | Pi boards | Secure shell | ✅ Active | ubuntu@192.168.50.1 / 10.8.5.150
7 |  | hostapd + WiFi Fix | 2.10 | ArmPi FPV | AP Hotspot | ✅ Active | SSID: ArmPi_AP ¦ PW: hiwonder ¦ 2.4GHz
8 |  | ChatGPT API | gpt-4o | TonyPi Pro | AI voice backend | 🔄 Setup | WonderEcho STT → GPT → TTS
ROBOTICS CONNECTION DETAILS & NETWORKING
# | Device | Connection Mode | IP Address | SSH Command | Password | VNC Viewer | SSID / Interface
1 | ArmPI FPV | ArmPi-AP (Hotspot) | 192.168.50.1 | ubuntu@192.168.50.1 | ubuntu123 | 192.168.50.1:1 | SSID: ArmPi_AP ¦ Password: hiwonder
2 | ArmPI FPV | Ethernet (Wired) | 10.8.5.150 | ubuntu@10.8.5.150 | ubuntu123 | 10.8.5.150:1 | eth0 ¦ Fast wired connection
3 | TonyPI Pro | TonyPi Pro | 192.168.149.1 | pi@192.168.149.1 | raspberrypi | 192.168.149.1:1 | Default
4 | Mecanum Chassis | Mecanum Chassis | N/A | N/A (USB Serial) | N/A | N/A | /dev/ttyUSB0 ¦ 9600 baud
5 | I Mac | Lab Mac (Client) | DHCP | N/A | N/A | RealVNC to robot IP | Connect Mac to ArmPi_AP Wi-Fi